# QUOTATION FOR REFUGEE LAW PROJECT

**Technology Stack:** Ruby on Rails with Joomla (as per requirement document) or Angular with bootstrap (Advised), Heruko or Amazon Web Services (Hosting) Payment/Donation APIs – Stripe or Beyonic

**Version Control:** Bitbucket (Considering the privacy)

**High Level Requirements:** Content, Funds, Domain Name, Web Hosting Services and SSL certificate

**Core Requirements Verses Cost Estimations**

|  |  |  |
| --- | --- | --- |
| **Requirement** | **Unit Cost** | **Total Cost (1 year)** |
| Domain | $20 per year | $20 |
| Web Hosting Services (Amazon or Heruko ) | $25 per month | $300 |
| SSL Certificate | $40 per year | $45 |
| **Grand Total** | | **$375** |

**Estimated Timeline Verses Development Costs**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Item/Feature** | **Duration (days)** | **Cost (USD)** | **Comments** |
| 1 | Front End Website | 5 | $450 |  |
| 2 | User Management (Registration authentication, User account management, Admin Account Management) | 6 | $540 |  |
| 3 | Data Analytics Module | 4 | $360 |  |
| 4 | Secure API information access on different access levels | 4 | $360 | This will be for strengthening security and all the data will accessed for this API |
| 5 | Video & Audio Managers (Upload, Players, Download, Search & Sort, Compatibility with devices & Management, Social Media Connection) | 10 | $900 |  |
| 6 | Document Manager (Upload, Reader, Search & Sort, Comment, download, Social Media Connection) | 6 | $540 |  |
| 7 | Photograph Manager (Upload, Download, View, Search & Sorting of photos, Social Media Connection ) | 5 | $450 |  |
| 8 | Donations and Payment Module | 6 | $540 |  |
| 9 | Search Engine Optimization, Social Media Connection, Visitors Tracker | 4 | $360 |  |
| 10 | Testing and Deployment | 3 | $270 |  |
| 11 | System User Manuals & User Training | 2 | $180 |  |
|  | **Total** | **55 days** | **$4950** |  |
|  |  |  |  |  |

**Important:**

|  |  |
| --- | --- |
| Immediately upon execution of this contract | 60% |
| Upon submission of working system according to the required specifications | 30% |
| Upon submission of final manuals & trainings | 10% |

**Note:**

1. All costs for servers, domains or charges by aggregators during payments or donations WILL NOT be inclusive of the development costs that has been charged by Lecodesoft Limited above but rather paid by Refugee Law Project (RLP)
2. Lecodesoft Limited is open to alternating Technology Stack before the execution of the contract if any other technology is a core requirement by Refugee Law Project